## Sheet1 - Table 1
Ph | Ref | Area | Pre-development Action | Next Step | Dev Units | Follow on work | Item | Description / Notes | Units per Release
2 | R20-01 | CRED |  | DONE | 0 |  | Add 'Custom Fields' tab to relevant components | This applies to TI and TIPP fields generated from Refine
2 | R20-02 | CRED |  | DONE | 0 |  | Add 'Requests for Data Review' tab to relevant components | Display on a 'Data Review' tab for each relevant component plus User. Implement based on links currently avaialble
2 | R20-03 | CRED |  | DONE | 0 |  | Filter 'Requests for Data Review' | Need to be able to filter the list - notably bu User and Status
2 | R20-04 | CRED |  | DONE | 0 |  | Auto-filter out Deleted items
2 | R20-05 | CRED |  | DONE | 0 |  | Remove 'Edit Status' and add 'Outstanding Review' | Replace with 'Outstanding Request for Review' (numeric field) in each component for which there is a Review tab; this field will be useful for reporting
2 | R20-07 | Ref Data |  | DONE | 0 |  | Update Ref Data values
2 | R20-071 | Ref Data |  | DONE | 0 |  | Add Variant Type values | Add Acronym, Minor Title Change
2 | R20-072 | Ref Data |  | DONE | 0 |  | Add Software ref data cat for Platforms | The Software with which platforms are associated (e.g. Atupon). Whilst Software could be a component, a Ref Data approach may be more practical
2 | R20-073 | Ref Data |  | DONE | 0 |  | Add Service ref data cat for Platforms | The Service with which platforms are associated (e.g. Highwire). Whilst Service could be a component, a Ref Data approach may be more practical
2 | R20-08 | Refine |  | DONE | 0 |  | Warnings on 'No publisher' | Error on column not present / Warning on blank values
2 | R20-09 | Refine |  | DONE | 0 |  | Incremental update & deletion of CRED TIPPs | Incremental update should not delete but should flag missing TIPPs for review. This might cause too much review work but we should see how it works out. A future approach could also flag TIPPs as never review / never delete
2 | R20-10 | Refine |  | DONE | 0 |  | Change 'DateFirstPackageIssue' error to warning | Currently 'DateFirstPackageIssue' generates an 'error' if it is not populated (as specified). Feedback says that a blank value in this column should only generate a 'warning'
2.1 | R21-01 | Refine | Owen/ Ian to identify method for correcting existing data | Owen | 0 | See - R30-02 | Make good the method for assuring suitable Platform names | This is required as a metter of urgency - funds are covered under item R30-02
2.1 | R21-02 | CRED | Review approach discussed on October 11 | Ian | 0 | See - R30-01 | ONIX-PL Licenses - Create metadata stub, display and download | Early POC implementation needed for Charleston (November 2013) - funds are covered under item R30-01
2.5 | R20-06 | Data |  | Ian | 0.5 |  | Tidy up non-authorised Orgs - some will be variants and others to be deleted | Remove non-authorised Orgs from current database, taking care where attached to a component; create as variants where applicable; include variants in Refine Org selection process
2.5 | R20-11 | Refine | Owen to establish with Kuali Wiki and kick off | Owen | 0.5 |  | GREL expressions guide, etc | Provide guide to expressions useful to 'novice' users. Use this to kick off a documentation Wiki
2.5 | R20-12 | Refine |  | SMEs | 0 |  | Agree how to make best use of Custom Fields for Title History | SMEs should work up a strategy for using Custom Fields to best advantage, especially for working with title history 'notes'
2.5 | R25-01 | Actions |  | Ian | 2 | See - R30-10 | Complete Title / TIPP Transfer action | Base on the NCSU meeting feedback
2.5 | R25-02 | Co-Ref |  | Ian | 3 |  | Expose persistent IDs for TIPPs | This needs reviewing as part of the API design
2.5 | R25-03 | Data |  | Ian | 0.5 |  | Delete KB+ Masterfile TIPPs and Packages - keep Tis | Remove TIPPs and Packages relating to the KB+ master files - but preserve TIs
2.5 | R25-04 | Data Model | Ian to review and propose spec | Ian | 4 |  | Preserve Package IDs across replacements | Links between Packages may be needed to serve a number of relationship use cases. We definitely need a peristent ID to track the 'Previous Package' relationship and to prevent unecessary proliferation of TIPPs. Note we still have no use case for implementing nested Package combos
2.5 | R25-05 | CRED | David to organise UI review starting 10-04 | Sero | 5 | See -R30-13 | UI Review - Priority actions arising | May include (a) Add 'distant' attributes that improve the display - e.g. Provider Name on TI form; (b) add SID component view with Namespace filter (notably for ISSN navigation)
2.5 | R25-06 | CRED |  | Ian | 2 |  | Add Create/Delete/Search for Variant Title & Variant Org Name
2.5 | R25-061 | CRED | Interim - able to edit TI name string in Ph2 | Ian | 3 |  | Approved / Variation list management | Would be better to include all variations including the Approved TI in the list and to flag one only as 'Approved', which is promoted to the TI heading
2.5 | R25-07 | CRED | David to organise search review starting 10-04 | Sero | 5 | Possibly | Develop Search interface (incl. technology choice and API requs) | Test Grails modules - may lead to a more substantial effort
2.5 | R25-09 | System wide | David to update spec | David | 2 |  | Add Source component | Develop Source > Project hierarchy in Refine (Source look-up) and CRED (Source CRUD)
2.5 | R25-10 | Refine | Owen to investigate with OpenRefine community | Ian | 2 |  | Strip white space throughout file | Get in the latest OpenRefine release or in the GOKb extension
2.5 | R25-11 | Refine | Steve to document existing and then investigate | Steve | 2 |  | Add a row | Adding a blank row to an existing Refine project should be an easily accessible function, being currently one of those things that is ‘easier in Excel’. At the moment to add a row in Refine you have to use the Split Multi-value function which is neither intuitive nor easily accessible
2.5 | R25-111 | Refine | Steve to document existing and then investigate | Steve | 1 |  | Remove rows
2.5 | R25-12 | Refine | Steve to investigate add column function | Steve | 2 |  | Missing column messages | Always give option to Rename or Add
2.5 | R25-14 | CRED |  | Ian | 0.5 |  | Indicator of number of list items in each Tab | A number on list-like Tabs representing the number of list items - this may not work well in all cases and will certainly need a text qualifier (e.g. 'N open items')
2.5 | R25-15 | CRED |  | Sero | 6 | Possibly | Apply permissions model to component CRUD actions | See 130503 data model review document - p3 | 41
3 | R25-08 | System wide | Owen to review ticketing systems to inform approach | Owen | 8 | Possibly | Develop Requests for Data Review functionality | Develop initial functionality to test practice on the assumption that data review is core GOKb functionality that should not be backed off to a ticketing system
3 | R30-01 | CRED | Complete work started under R21-02 - Seldon has the requirements | Ian | 3 | Possibly | ONIX-PL Licenses - Create metadata stub, display and download | See notes for conversation with Seldon on October 11, 2013
3 | R30-02 | System wide | Sero & K-Int to propose spec by 10/31 | Sero | 12 |  | Introduce TIP - no Package - in to data model | Benefits include handling of platforms and generation of TIP IDs - see 08/24 discussion notes
3 | R30-021 | System wide |  |  | 2 |  | Platform attributes and combos | Platforms needs to be more richly described in terms of Types, Combos, date ranges, etc.
3 | R30-03 | API |  | OLE | 10 |  | Step 1 - Create New Packages, Platforms, Orgs | OLE to drive spec - export format to be decided (ONIX-KB XML, KBART CSV, JSON). OLE & KB+ both expect this in 2013
3 | R30-03 | API | KB+ pays for this | KB+ | 7 |  | Step 2 - Refresh Packages, Platforms, Orgs | KB+ to drive spec - KB+ needs this back-to-back with Create New
3 | R30-05 | Data Model | Rules to be reviewed by SMEs | Owen | 3 |  | Master List generation and storage | Publisher Master Lists need to be periodically generated and physically stored to support API requirements; to be displayed at top of list in CRED
3 | R30-06 | CRED |  | Sero | 7 |  | CRUD of TI history relationships including meaningful display | The relationships and their directions are potentially confusing - so possibly best presented in a 'sentence' format
3 | R30-11 | Data model | Review use cases and develop specification | Sero | 2 |  | TIPP combos | To allow expression of ‘comes with’ type relationships between TIPPs
3 | R30-12 | Data Model | Confirm model | Sero | 2 |  | Imprint | Imprints are not Orgs so may be best dealt with as a new Component linked directly to both TI and Org
3 | R30-132 | CRED |  | Ian | 1 |  | Switching Approved Package Name with Variation | As per Variant Title | 57
3.5 | R25-12 | Refine | Steve to document existing and then investigate | Steve | 3 |  | Delete multiple columns | Make it easier to delete multiple columns. This is supported a little in Refine but not in one go, and the function is not obvious
3.5 | R25-13 | CRED | Gill and Helen to develop approach | Gill | 5 | Possibly | Adopt UI skin - color scheme and branding | Assume 1 iteration based on e-Matrix template
3.5 | R30-07 | Data Model |  | Ian | 0.5 |  | Variant name for Packages
3.5 | R30-071 | Refine |  | Steve | 0.5 |  | Package look-up to include variant name and quick create | Variant name as per Variant Org
3.5 | R30-08 | Refine | Scoping document | Ian | 5 |  | Reuse of shared rules within Refine | Ability for users to select rules for reuse - e.g. filter rules and get suggested operations based on such as provider, file type or rule type; nb includes access in rules CRED. For safety, this would require some description of each reusable rule
3.5 | R30-09 | Refine | Review feasible approaches | Owen | 4 |  | Bulk publisher validation | There needs to be a much more optimal way of doing this for such as Aggregator files
3.5 | R30-10 | Actions | Review the list of priority use cases in light of R25-01 | Sero | 12 | Possibly | Develop the priority action use cases | Base the specification for the other (seven?) priority actions on the approach established in the Title / TIPP Transfer example
3.5 | R30-13 | CRED |  | Sero | 5 | Possibly | UI Review - Actions carried forward from R25-05 | This selects priorities from the backlog not fixed in R25-05
3.5 | R30-131 | CRED |  | Sero | 3 |  | Filtering of lists | Add filtering on key fields in lists or handle through alternative mechanism such as Search
3.5 | R30-14 | Doc | Agree & implement documentation approach | Sero | 2 |  | Add Tips / Hints to forms | These will need to be populated
3.5 | R30-15 | Co-Ref | Develop a set of use cases to inform | Sero | 8 | Possibly | Expose Co-Ref service | In order to gain traction this needs to be dome with specific use cases / users (e.g. Publishers or KBs) in mind
3.5 | R30-16 | Ref Data | See discussion thread | Ian | 2 |  | Ref Data Category Labels | Make re-labelling easier | 50
4 | R30-04 | API | Owen worrk with SMEs to define use cases | Owen | 2 |  | Support 'Random Lists' export | See package example from Ben Heet - potentially integrated with Search
4 | R40-01 | API | KB+ pays for this | KB+ | 6 | Possibly | Phase 3 - Feedback corrected datasets (Roundtrip) to GOKb | KB+ to drive spec - potentially using Onix-KB. This is fundamental to the GOKb vision but is not as urgent for downstream partners
4 | R40-02 | API |  | OLE | 3 | Possibly | Phase 4 - Feedback atomic local library corrections to GOKb | OLE to drive spec - useful for individual libraries to promote individual errors back to GOKb (e.g. TIPP not in Package, Date error)
4 | R40-03 | Refine | Feasibility assessment required - Custom Fields to be used in meantime | Owen | 5 |  | Import for Title changes | To be accomplished through Refine if feasible - beware edge cases
4 | R40-04 | Refine | Owen investigate with OpenRefine community | Owen | 2 |  | Improve Cell editing | In Excel you can just click in a cell and type. In Refine you have to find the right button, then click, then edit, then save
4 | R40-06 | System wide | David to propose process to sign off final backlog | Sero | 20 | Yes | Clear product backlog | This will includes possible 'follow on work' | 38
5 | R50-01 | Comms & Collab | Review approach used in KB+ | All | ? |  | Alerts, Discussion and related editorial and community functionality | Beyond current grant
5 | R05-nn | System wide |  | All | ? |  | Items as yet undefined | Beyond current grant
x | R40-05 | CRED | Not needed | N/A | 0 |  | ONIX-PL Pt 2 - Traffic lights and full licence navigation and comparison | Draw on KB+ developments
x | SMEs | Data Model | Not needed | N/A | 0 |  | Organisation History | Clarification - We are tracking TI relationships with Orgs; we are not committed to tracking canonical organisation relationships, changes and reasons
x | SMEs | Data Model | Not needed | N/A | 0 |  | Package within Package
| Total |  |  |  | 186 |  |  |  | 186